## Sheet1
PROJECT PART 4 TIMELINE | Oct. 15 | Oct. 17 | Oct. 19 | Oct. 21 | Oct. 23 | Oct. 25 | Oct. 27 | Oct. 29 | Oct. 31 | Nov. 2 | Nov. 4 | Nov. 6 | Nov. 8 | Nov. 10 | Nov. 12 | Nov. 14
CreateNewHabit | bar: Oct. 15 to Oct. 19
ViewHabitDetails | bar: Oct. 17 to Oct. 21
DeleteHabit | bar: Oct. 17 to Oct. 23
EditHabit | bar: Oct. 19 to Oct. 23
ViewHabitList | bar: Oct. 21 to Oct. 25
CreateHabitEvent | bar: Oct. 23 to Oct. 27
ViewHabitEventDetails | bar: Oct. 25 to Oct. 29
DeleteHabitEvent | bar: Oct. 27 to Nov. 2
EditHabitEvent | bar: Oct. 27 to Nov. 4
ViewHabitHistory | bar: Oct. 29 to Nov. 6
ProfileSignup | bar: Oct. 29 to Nov. 6
ProfileLogin | bar: Oct. 31 to Nov. 6
Testing | bar: Nov. 2 to Nov. 12
Bugfixing | bar: Nov. 2 to Nov. 12
PROJECT PART 5 TIMELINE | Nov. 14 | Nov. 16 | Nov. 18 | Nov. 20 | Nov. 22 | Nov. 24 | Nov. 26 | Nov. 28 | Nov. 30 | Dec. 2 | Dec. 4
HabitStatusIndicator | bar: Nov. 14 to Nov. 16
AddPhotoHabitEvent | bar: Nov. 14 to Nov. 18
FilterHabitHistoryType | bar: Nov. 16 to Nov. 18
FilterHabitHistoryComment | bar: Nov. 16 to Nov. 18
RequestFollow | bar: Nov. 16 to Nov. 20
GrantFollow | bar: Nov. 16 to Nov. 20
ViewFollowers | bar: Nov. 18 to Nov. 20
ViewFollowing | bar: Nov. 18 to Nov. 20
AddLocationHabitEvent | bar: Nov. 20 to Nov. 22
ViewMapHabitEvents | bar: Nov. 20 to Nov. 24
HighlightNearbyHabitEvents | bar: Nov. 22 to Nov. 24
SynchOfflineChanges | bar: Nov. 24 to Nov. 26
Extra Features | bar: Nov. 26 to Nov. 30
Testing | bar: Nov. 28 to Dec. 4
Bugfixing | bar: Nov. 28 to Dec. 4